## Sheet1
Task ID | Task Description | Category | Priority | Status | Notes | Link to FYP1 Report: | https://docs.google.com/document/d/1rVbWoatZkmNisgtaDAgxFU5iTkoyqhf5CVGZ_pejgjM/edit?usp=sharing
PHASE 1A: LITERATURE REVIEW
T001 | Define literature search strategy | Research | High | DONE
T002 | Collect 10 academic papers (Batch 1) | Research | High | DONE
T003 | Collect 10 academic papers (Batch 2) | Research | High | DONE
T004 | Read & categorize all 20 papers | Research | High | DONE
T005 | Deep read papers 1-5 with notes | Research | Critical | DONE
T006 | Deep read papers 6-15 with notes | Research | Critical | DONE
T007 | Deep read papers 16-20 with notes | Research | Critical | DONE
T008 | Literature analysis & synthesis | Research | Critical | DONE
T009 | Define target audience & personas | Research | High | DONE
PHASE 1B: REQUIREMENTS & USE CASES
T010 | Review & simplify use cases | Requirements | Critical
T011 | Finalize functional requirements | Requirements | Critical
T012 | Create use case diagram (UML) | Requirements | High
T013 | Write detailed use case descriptions | Requirements | High
PHASE 1C: UML DIAGRAMS
T014 | Create class diagram | Design | Critical
T015 | Create sequence diagrams (3 scenarios) | Design | High
T016 | Create DFD Level 0 & 1 | Design | High
T017 | Create ERD | Design | Critical
T018 | Create architecture diagram | Design | Critical
T019 | Create activity/state diagrams | Design | Medium
T020 | Organize & push all docs to GitHub | Design | High